## PROJECT PLAN
ONE PEOPLE FUNDRAISER EVENT (PROJECT PLAN) Objective: To Promote Unity among Youths with various cultural Diversity | time axis 2024-07-21 to 2024-10-31
Category | Action item/Deliverables | Owner | Start Date | End Date | Status
Team Meeting | Meeting to discuss the project and assign tasks for the successful execution | Project Manager | 2024-07-23 | 2024-07-23 | Done | 2024-07-23: Done
Budget Development | Setting up a well-articulated budget for the project execution | Finance Manager | 2024-07-23 | 2024-08-08 | Done | 2024-07-23: Done; 2024-07-24: Done; 2024-07-25: Done; 2024-07-26: Done; 2024-07-27: Done; 2024-07-28: Done; 2024-07-29: Done; 2024-07-30: Done; 2024-07-31: Done; 2024-08-01: Done; 2024-08-02: Done; 2024-08-03: Done; 2024-08-04: Done; 2024-08-05: Done; 2024-08-06: Done; 2024-08-07: Done; 2024-08-08: Done
Event Planning and Logistics | Secure a venue, decide on the date and time, set up the theme, manage permits, coordinate rentals etc. | Me (Event Coordinator) | 2024-07-23 | 2024-08-08 | Done | 2024-07-23: Done; 2024-07-24: Done; 2024-07-25: Done; 2024-07-26: Done; 2024-07-27: Done; 2024-07-28: Done; 2024-07-29: Done; 2024-07-30: Done; 2024-07-31: Done; 2024-08-01: Done; 2024-08-02: Done; 2024-08-03: Done; 2024-08-04: Done; 2024-08-05: Done; 2024-08-06: Done; 2024-08-07: Done; 2024-08-08: Done
Sponsorship and Partnerships | Identify and reach out to potential sponsors, negotiate sponsorship agreements and handle follow ups | Sponsorship Coordinator | 2024-07-23 | 2024-08-08 | Done | 2024-07-23: Done; 2024-07-24: Done; 2024-07-25: Done; 2024-07-26: Done; 2024-07-27: Done; 2024-07-28: Done; 2024-07-29: Done; 2024-07-30: Done; 2024-07-31: Done; 2024-08-01: Done; 2024-08-02: Done; 2024-08-03: Done; 2024-08-04: Done; 2024-08-05: Done; 2024-08-06: Done; 2024-08-07: Done; 2024-08-08: Done
Marketing and Promotion | Develop and implement a marketing plan and coordinate email campaigns to promote the event. | Marketing Lead | 2024-08-05 | 2024-08-19 | Done | 2024-08-05: Done; 2024-08-06: Done; 2024-08-07: Done; 2024-08-08: Done; 2024-08-09: Done; 2024-08-10: Done; 2024-08-11: Done; 2024-08-12: Done; 2024-08-13: Done; 2024-08-14: Done; 2024-08-15: Done; 2024-08-16: Done; 2024-08-17: Done; 2024-08-18: Done; 2024-08-19: Done
Content Creation and Graphic Design | Development of promotional materials (flyers, banners, social media posts) for the event | Marketing Lead | 2024-08-04 | 2024-08-10 | Done | 2024-08-04: Done; 2024-08-05: Done; 2024-08-06: Done; 2024-08-07: Done; 2024-08-08: Done; 2024-08-09: Done; 2024-08-10: Done
Guest and Ticket Management | Handle RSVPs and ticket sales, manage online registration, send confirmation emails | Guest Relations Manager | 2024-08-11 | 2024-09-08 | Done | 2024-08-11: Done; 2024-08-12: Done; 2024-08-13: Done; 2024-08-14: Done; 2024-08-15: Done; 2024-08-16: Done; 2024-08-17: Done; 2024-08-18: Done; 2024-08-19: Done; 2024-08-20: Done; 2024-08-21: Done; 2024-08-22: Done; 2024-08-23: Done; 2024-08-24: Done; 2024-08-25: Done; 2024-08-26: Done; 2024-08-27: Done; 2024-08-28: Done; 2024-08-29: Done; 2024-08-30: Done; 2024-08-31: Done; 2024-09-01: Done; 2024-09-02: Done; 2024-09-03: Done; 2024-09-04: Done; 2024-09-05: Done; 2024-09-06: Done; 2024-09-07: Done; 2024-09-08: Done
Team Meeting | presentation of reports on assigned tasks, discussion of challenges faced (if any) | Project Manager | 2024-08-01 | 2024-08-01 | Done | bar: 2024-08-01
Volunteer Coordination | Recruit, train, manage and oversee volunteer activities to ensure everything runs smoothly | Volunteer Coordinator | 2024-08-02 | 2024-09-10 | Done | 2024-08-02: Done; 2024-08-03: Done; 2024-08-04: Done; 2024-08-05: Done; 2024-08-06: Done; 2024-08-07: Done; 2024-08-08: Done; 2024-08-09: Done; 2024-08-10: Done; 2024-08-11: Done; 2024-08-12: Done; 2024-08-13: Done; 2024-08-14: Done; 2024-08-15: Done; 2024-08-16: Done; 2024-08-17: Done; 2024-08-18: Done; 2024-08-19: Done; 2024-08-20: Done; 2024-08-21: Done; 2024-08-22: Done; 2024-08-23: Done; 2024-08-24: Done; 2024-08-25: Done; 2024-08-26: Done; 2024-08-27: Done; 2024-08-28: Done; 2024-08-29: Done; 2024-08-30: Done; 2024-08-31: Done; 2024-09-01: Done; 2024-09-02: Done; 2024-09-03: Done; 2024-09-04: Done; 2024-09-05: Done; 2024-09-06: Done; 2024-09-07: Done; 2024-09-08: Done; 2024-09-09: Done; 2024-09-10: Done
Entertainment and Program Management | Arrange speakers, entertainment, and activities for the event, create a detailed program schedule, and coordinate | Me (Event Coordinator) and Project Manager | 2024-08-04 | 2024-09-28 | Done | 2024-08-04: Done; 2024-08-05: Done; 2024-08-06: Done; 2024-08-07: Done; 2024-08-08: Done; 2024-08-09: Done; 2024-08-10: Done; 2024-08-11: Done; 2024-08-12: Done; 2024-08-13: Done; 2024-08-14: Done; 2024-08-15: Done; 2024-08-16: Done; 2024-08-17: Done; 2024-08-18: Done; 2024-08-19: Done; 2024-08-20: Done; 2024-08-21: Done; 2024-08-22: Done; 2024-08-23: Done; 2024-08-24: Done; 2024-08-25: Done; 2024-08-26: Done; 2024-08-27: Done; 2024-08-28: Done; 2024-08-29: Done; 2024-08-30: Done; 2024-08-31: Done; 2024-09-01: Done; 2024-09-02: Done; 2024-09-03: Done; 2024-09-04: Done; 2024-09-05: Done; 2024-09-06: Done; 2024-09-07: Done; 2024-09-08: Done; 2024-09-09: Done; 2024-09-10: Done; 2024-09-11: Done; 2024-09-12: Done; 2024-09-13: Done; 2024-09-14: Done; 2024-09-15: Done; 2024-09-16: Done; 2024-09-17: Done; 2024-09-18: Done; 2024-09-19: Done; 2024-09-20: Done; 2024-09-21: Done; 2024-09-22: Done; 2024-09-23: Done; 2024-09-24: Done; 2024-09-25: Done; 2024-09-26: Done; 2024-09-27: Done; 2024-09-28: Done
Team Meeting | Meeting 3 days before the event day to ensure that all is ready to go | Project Manager | 2024-09-05 | 2024-09-05 | Done | 2024-09-05: Done